## Master Overview
NEXUS PORTAL — PRODUCTION ROADMAP (16-WEEK POLYREPO BUILD)
Generated 2026-09-30 · Start Monday 2026-10-05 · Polyrepo microservices decision (2026-09-30): 10 service repos, GLOW-AI style — see Tech Debt & Risks
WORKSTREAM | PHASE 1: FOUNDATION — POLYREPO SPLIT, RBAC & ROUTE INTEGRATION |  |  |  | PHASE 2: COMMAND CENTRE & DOMAIN SERVICES |  |  |  | PHASE 3: REAL INTEGRATIONS & WRITE WORKFLOWS |  |  |  | PHASE 4: PRODUCTION HARDENING & OFFLINE RESILIENCE
Week / date range → | W01 05–09 Oct | W02 12–16 Oct | W03 19–23 Oct | W04 26–30 Oct | W05 02–06 Nov | W06 09–13 Nov | W07 16–20 Nov | W08 23–27 Nov | W09 30 Nov–04 Dec | W10 07–11 Dec | W11 14–18 Dec | W12 21–25 Dec | W13 28 Dec–01 Jan | W14 04–08 Jan | W15 11–15 Jan | W16 18–22 Jan
⚙ Settings & Config | Unify tenant/env config consolidate .env.example + backend pydantic-settings | Path aliases (tsconfig) @components/@hooks/@services per FOLDER_STRUCTURE.md | Shared constants pass roles.ts, strings.ts (frontend) | PHASE 1 GATE prep config review | Feature-flag scaffold (module status toggles) |  |  |  | Webhook secrets config (easiPol sandbox creds) |  |  |  | Staging env config (.env.staging)
🧱 Polyrepo & Service Extraction [NEW] | Create 10 repos under KamiSolutions (gateway, identity, financials, hr, fleet, cases, claims, audit, platform, infra) | Extract nexus-identity- service from monolith (rbac.py, security.py, tenant deps) | Extract nexus-financials- service (financials.py, policy_service.py) | PHASE 1 GATE nexus-api-gateway routes identity + financials as real deployed services | Extract nexus-hr-service + nexus-fleet-service (currently empty stubs) | Extract nexus-cases- service + nexus-claims- service (new domains) | nexus-audit-service: cross-cutting, written to by every other service | PHASE 2 GATE all domain services deployed independently | Service-to-service auth: gateway-issued short-lived internal tokens |  |  |  | nexus-platform-service: Command Centre BFF, fans out to domain services
🔐 Unified RBAC & Roles ⬆ DONE (pre-sprint) | ✅ DONE (pre-sprint) Combined role model shipped lib/permissions.ts + rbac.py DRIVER + MORTUARY_STAFF added | Route-level guard: real RoleProtected.tsx (was empty, nav-hide only) | useAuth / useRole hooks wired to JWT payload (sub, scopes, tenant_id, role) | PHASE 1 GATE RBAC end-to-end demo (4 role tokens, 4 outcomes) | Per-tenant role assignment (not global) | Admin: role management screen (assign/revoke) |  |  | Field-role scoping: DRIVER sees own vehicle only (row filter)
🗄 Data Models & Persistence | Schema review vs. Pydantic v2 models (finance, tenant, auth) | Postgres migration plan (replace in-memory tenant registry) | SQLAlchemy async models finance + tenant tables | Alembic migrations init + seed data | HR + vehicles models | Cases (mortuary) model [NEW module] | Leases + policies models | PHASE 2 GATE full schema migrated | Audit log table (append-only, indexed)
🧭 Multi-Tenancy | ✅ DONE (pre-sprint) get_tenant_context X-Tenant-ID + demo_sandbox fallback, fail-closed 404 | Tenant registry → real DB-backed lookup (replaces in-memory dict) | Shared vs dedicated deployment_mode branch in service layer | PHASE 1 GATE tenant isolation test (cross-tenant 404 proof) |  |  |  |  | Dedicated-tenant provisioning script (AVBOB-scale onboarding)
🧩 Frontend Route Integration | Audit legacy vs (workspace) screens — map what moves where | Finance sub-routes: requisitions, pending, approved, loan | HR sub-routes: leave, contracts | PHASE 1 GATE Claims + vehicles maintenance sub-routes | Retire legacy flat routes + old Sidebar.tsx + (tabs) grid | FileUpload.tsx audit — port reusable logic or replace
📊 Command Centre / Overview |  |  |  |  | Status model: Operational / Attention Required / Unknown + stated reason (schema) | Backend: /api/v1/overview aggregates module status | Frontend: replace ExecutiveDashboard's fake activity feed + AI insight with real aggregation | PHASE 2 GATE Command Centre demo (honest status, no fake data) | Attention-required feed: lapsed policies, overdue maintenance, expired tokens
🔌 Integrations Layer |  |  |  |  | Adapter interface design (Provider → Integration Layer → Nexus data) | Settings screen fix: remove fake Xero/SharePoint/ O365 → “Not connected—demo” for easiPol/EasyPay/Sage |  |  | First real adapter: easiPol sandbox end-to-end | Adapter status surfaced in Command Centre (last-sync, auth expiry) | EasyPay/Pay@ webhook receiver (sandbox) | PHASE 3 GATE one real integration, honest status everywhere
📋 Audit & Compliance (POPIA/FSCA) |  |  |  |  | Audit log schema (user, tenant, action, timestamp, payload) | Write audit entries in-transaction with state changes (not fire-and-forget) | Audit/Activity screen (replaces decorative chip in ModuleOverview) | PHASE 2 GATE audit trail demo | Redis short-TTL cache design (data federation for sensitive fields) | Data federation: policy PII not persisted, masked + cached only
🚗 Domain Services (write layer) |  |  |  |  | nexus-fleet-service: vehicles router (2nd service, proves financials pattern) | nexus-hr-service: router (leave, contracts) | nexus-cases-service: router [NEW domain] | PHASE 2 GATE 2+ services on real async read pattern, reachable via gateway | POST/PUT/DELETE mutators (finance, HR) | Webhook processor: /policies/webhook/easipol | BackgroundTasks: policy status → auto logistics scheduling | PHASE 3 GATE write path + webhook end-to-end
🐳 Docker & Infra / CI-CD (per-service) | nexus-infra repo: shared CI workflow template (reused by every service repo) | Per-service Dockerfile + root docker-compose (gateway + identity + financials + Postgres) | CI: lint + test on push, per repo (GitHub Actions reusable workflow) | PHASE 1 GATE CI green on all repos created so far, containers boot clean via compose | docker-compose grows: +hr, +fleet services | docker-compose grows: +cases, +claims services |  |  | Terraform: ECS/RDS/ ElastiCache skeleton (nexus-infra) |  |  |  | Staging compose (all 9 services) + docker-compose.staging.yml | Deploy pipeline per service (build → push → deploy, independent versioning) | Secrets management (no .env in staging, per-service secrets) | PHASE 4 GATE CI/CD green across all repos, staging stable
🧪 Testing | Backend: pytest scaffold + RBAC/tenant tests (the 6 cases already verified manually) | Frontend: RoleProtected unit tests (route guard) | Integration test: full auth → scope → endpoint flow | PHASE 1 GATE coverage baseline set |  |  |  | Command Centre + domain router tests |  |  |  | Integration adapter tests (sandbox) |  |  |  | Load test + security regression pass
🌐 Frontend State & Auth |  | Real login flow (replace no-op button with actual auth call) | AuthProvider → real token storage, not hardcoded demo user |  | Zustand migration: auth + permissions stores first | Zustand migration: tenant + workspace stores | Remaining ad hoc store/* migrated | PHASE 2 GATE no hardcoded demo state left in providers
📴 Offline & Sync | [12 empty] | SQLite/MMKV local persistence layer (design) | Reconnect queue: queued actions replay on network return | Batch ingestion endpoint /api/v1/sync/batch | PHASE 4 GATE offline round-trip demo (field → sync)
🖨 Document Generation | [13 empty] | ReportLab scaffold + template design | Statutory documents: death certificates, DHA-1663 notices | Lease agreement PDF export + PHASE 4 GATE
◆ PHASE GATE CRITERIA | PHASE 1 GATE — End W04 ✓ 10 repos created under KamiSolutions, nexus-identity-service + nexus-financials-service extracted and independently deployed · nexus-api-gateway routes to both as real services (not in-process routers) · combined role model live end-to-end · route-level RBAC guard (not nav-hiding only) · legacy Finance/HR/Claims/Vehicles sub-routes integrated · tenant isolation proven · CI green on every repo created so far ⚠ BLOCKED pending repo creation — see Open Items |  |  |  | PHASE 2 GATE — End W08 ✓ Command Centre shows real Operational/Attention-Required/Unknown status · fake activity feed + fake integrations removed · 2+ modules on the async router pattern · audit trail writing in-transaction |  |  |  | PHASE 3 GATE — End W12 ✓ One real integration adapter (easiPol) end-to-end, honestly labeled everywhere else · write endpoints + webhook live · POPIA data-federation cache in place |  |  |  | PHASE 4 GATE — End W16 ✓ Staging deployed · CI/CD green · offline round-trip demoed · statutory document export working · client/Technical Manager demo-ready
Overall readiness % | 8% | 14% | 20% | 27% | 34% | 41% | 48% | 55% | 62% | 68% | 74% | 79% | 84% | 89% | 94% | 100%
Public holidays (SA) | [10 empty] | Day of Reconciliation | Christmas Day | New Year's Day

## Daily Execution
Week | Date | Track | Task | Files / repo touched
W01 | Mon 05 Oct | Polyrepo | ⚠ BLOCKED on user: create 10 repos under KamiSolutions (gateway, identity, financials, hr, fleet, cases, claims, audit, platform, infra) — this session's GitHub access is repo-scoped, cannot create org repos itself | github.com/KamiSolutions/*
W01 | Tue 06 Oct | Settings | Consolidate .env.example + backend pydantic-settings config | lib/*.ts · app/core/config.py
W01 | Wed 07 Oct | RBAC | ✅ DONE (pre-sprint, verified today) — combined role model (EnterpriseRole + PermissionModule extended: DRIVER, MORTUARY_STAFF, cases) and backend scopes re-keyed to module:action strings (finance:view replaces financials:read) | lib/permissions.ts · app/core/rbac.py · security.py
W01 | Thu 08 Oct | Multi-Tenancy | ✅ DONE (pre-sprint, verified) — get_tenant_context: X-Tenant-ID + demo_sandbox fallback, fail-closed 404 on unknown tenant | app/dependencies/tenant.py
W01 | Fri 09 Oct | Testing | Backend pytest scaffold covering the 6 manually-verified cases (200/401/403/404 x tenant/scope combos) | tests/test_auth.py · test_tenant.py
W02 | Mon 12 Oct | Frontend Routes | Audit legacy vs (workspace) screens — map exactly what content moves where | app/(legacy)/* · app/(workspace)/*
W02 | Tue 13 Oct | Auth | Replace no-op login button with a real auth call against the backend | app/(auth)/login.tsx
W02 | Wed 14 Oct | RBAC | Build real RoleProtected.tsx (route-level guard) — was a genuinely empty 0-byte file | app/components/RoleProtected.tsx
W02 | Thu 15 Oct | Infra | CI: lint + test on push | .github/workflows/ci.yml
W02 | Fri 16 Oct | Config | Path aliases in tsconfig.json per FOLDER_STRUCTURE.md proposal | tsconfig.json
W03 | Mon 19 Oct | Frontend Routes | Fold financials/requisitions.tsx, pending.tsx, approved.tsx, loan.tsx into (workspace)/finance/* | app/(workspace)/finance/*
W03 | Tue 20 Oct | Auth | AuthProvider: real token storage replacing hardcoded demo user | providers/AuthProvider.tsx
W03 | Wed 21 Oct | Data Models | SQLAlchemy async models: finance + tenant tables | app/models/finance.py · tenant.py
W03 | Thu 22 Oct | Testing | Integration test: full auth → scope → endpoint flow | tests/test_integration.py
W03 | Fri 23 Oct | Frontend Routes | Fold hr/leave.tsx, hr/contracts.tsx into (workspace)/hr/* | app/(workspace)/hr/*
W04 | Mon 26 Oct | Frontend Routes | Fold policies/claim.tsx → (workspace)/policies/claim, vehicles/maintenance.tsx → (workspace)/vehicles/maintenance | app/(workspace)/policies/* · vehicles/*
W04 | Tue 27 Oct | Data Models | Alembic migrations: init + seed data | alembic/versions/*
W04 | Wed 28 Oct | Multi-Tenancy | Tenant isolation proof test: cross-tenant request → 404, never leaked data | tests/test_tenant_isolation.py
W04 | Thu 29 Oct | Infra | Docker: backend Dockerfile + docker-compose (FastAPI + Postgres) | Dockerfile · docker-compose.yml
W04 | Fri 30 Oct | PHASE 1 GATE | Gate review: RBAC end-to-end, route integration proven, CI green, tenant isolation demonstrated | ALL — gate complete
W05 | Mon 02 Nov | Command Centre | Design status model: Operational / Attention Required / Unknown + stated reason (Pydantic schema) | app/schemas/status.py
W05 | Tue 03 Nov | State Mgmt | Zustand migration: auth + permissions stores first | store/auth/* · permissions/*
W05 | Wed 04 Nov | Legacy Cleanup | Retire old flat routes + Sidebar.tsx + (tabs) grid now that content has moved | app/dashboard.tsx · app/(tabs)/* · app/components/Sidebar.tsx
W05 | Thu 05 Nov | Domain Routers | Vehicles/fleet router — second module proving the financials pattern generalizes | app/api/v1/vehicles.py
W05 | Fri 06 Nov | Audit | Audit log schema: user, tenant, action, timestamp, payload | app/models/audit_log.py
W06 | Mon 09 Nov | Command Centre | Backend: /api/v1/overview aggregates module status across finance + vehicles | app/api/v1/overview.py
W06 | Tue 10 Nov | Integrations | Settings screen fix: remove fake Xero/SharePoint/O365 → honest “Not connected — demo mode” for easiPol/EasyPay/Sage | app/(workspace)/settings/index.tsx
W06 | Wed 11 Nov | Audit | Write audit entries in the same DB transaction as the state change (not fire-and-forget) | app/services/*/[…]_service.py
W06 | Thu 12 Nov | State Mgmt | Zustand migration: tenant + workspace stores | store/tenant/* · workspace/*
W06 | Fri 13 Nov | Data Models | Cases (mortuary) model — new module, no prior representation | app/models/cases.py
W07 | Mon 16 Nov | Command Centre | Frontend: replace ExecutiveDashboard's hardcoded activity feed + fabricated “AI insight” with real aggregated data | components/dashboard/ExecutiveDashboard.tsx
W07 | Tue 17 Nov | Domain Routers | HR router (leave, contracts) on the async pattern | app/api/v1/hr.py
W07 | Wed 18 Nov | Audit | Audit/Activity screen — replaces the decorative, non-functional chip in ModuleOverview | app/(workspace)/audit/index.tsx
W07 | Thu 19 Nov | State Mgmt | Remaining ad hoc store/* modules migrated to Zustand | store/*
W07 | Fri 20 Nov | Domain Routers | Cases (mortuary) router — new module | app/api/v1/cases.py
W08 | Mon 23 Nov | PHASE 2 GATE | Command Centre demo: real status, no fake data anywhere in the dashboard | ALL — gate complete
W08 | Tue 24 Nov | Testing | Command Centre + domain router test coverage | tests/test_overview.py · test_vehicles.py · test_hr.py
W08 | Wed 25 Nov | Data Models | Full schema migrated across finance, HR, vehicles, cases, tenant | alembic/versions/*
W08 | Thu 26 Nov | State Mgmt | Confirm no hardcoded demo state remains in any provider | providers/*
W09 | Mon 30 Nov | Integrations | First real adapter: easiPol sandbox connection, end-to-end | app/services/integrations/easipol.py
W09 | Tue 01 Dec | Domain Routers | POST/PUT/DELETE mutators: finance + HR | app/api/v1/finance.py · hr.py
W09 | Wed 02 Dec | Audit | Redis short-TTL cache design (POPIA data federation for sensitive fields) | app/core/cache.py
W09 | Thu 03 Dec | RBAC | Field-role scoping: DRIVER sees only their own assigned vehicle (row-level filter) | app/services/vehicles/*
W09 | Fri 04 Dec | Command Centre | Attention-required feed: lapsed policies, overdue maintenance, expired integration tokens | app/services/overview_service.py
W10 | Mon 07 Dec | Integrations | Adapter status surfaced in Command Centre: last-sync time, auth expiry, connection state | app/api/v1/overview.py
W10 | Tue 08 Dec | Domain Routers | Webhook processor: POST /api/v1/policies/webhook/easipol | app/api/v1/policies.py
W10 | Wed 09 Dec | Audit | Data federation live: policy PII fetched + masked + cached, never persisted long-term | app/services/policies/federation.py
W10 | Thu 10 Dec | Multi-Tenancy | Dedicated-tenant provisioning script (AVBOB-scale onboarding path) | scripts/provision_dedicated_tenant.py
W11 | Mon 14 Dec | Integrations | EasyPay/Pay@ webhook receiver (sandbox) | app/api/v1/billing.py
W11 | Tue 15 Dec | Domain Routers | BackgroundTasks: policy status change auto-schedules logistics dispatch | app/services/policies/workflows.py
W11 | Thu 17 Dec | [PH] | Day of Reconciliation (16 Dec) — public holiday, 4-day week | —
W11 | Fri 18 Dec | Testing | Integration adapter tests against easiPol sandbox | tests/test_easipol_adapter.py
W11 | Wed 16 Dec | [Public Holiday] | Day of Reconciliation — office closed, not a working day | —
W12 | Mon 21 Dec | PHASE 3 GATE | One real integration end-to-end, everything else still honestly labeled “not connected”, write path + webhook proven | ALL — gate complete
W12 | Tue 22 Dec | [Holiday] | Christmas Day (25 Dec) — public holiday, 4-day week. Reduced-capacity buffer/QA week. | —
W12 | Wed 23 Dec | Docs | Mid-roadmap documentation sweep: API.md, ARCHITECTURE.md draft | docs/*.md
W12 | Fri 25 Dec | [Public Holiday] | Christmas Day — office closed, not a working day | —
W13 | Mon 28 Dec | [Holiday] | New Year's Day (1 Jan) — public holiday, 4-day week. Year-end period — planned low-capacity buffer. | —
W13 | Tue 29 Dec | Offline | SQLite/MMKV local persistence layer — design | lib/offline/*
W13 | Wed 30 Dec | Infra | Staging compose (docker-compose.staging.yml) | docker-compose.staging.yml
W13 | Thu 31 Dec | Docs | DEPLOYMENT.md draft | docs/DEPLOYMENT.md
W13 | Fri 01 Jan | [Public Holiday] | New Year's Day — office closed, not a working day | —
W14 | Mon 04 Jan | Offline | Reconnect queue: actions queued offline replay automatically on reconnect | lib/offline/queue.ts
W14 | Tue 05 Jan | Infra | Deploy pipeline: build → push → deploy | .github/workflows/deploy.yml
W14 | Wed 06 Jan | Documents | ReportLab scaffold + template design | app/services/documents/*
W14 | Thu 07 Jan | Testing | End-to-end offline → sync round-trip test | tests/test_offline_sync.py
W15 | Mon 11 Jan | Offline | Batch ingestion endpoint: POST /api/v1/sync/batch | app/api/v1/sync.py
W15 | Tue 12 Jan | Infra | Secrets management for staging — no .env committed or shipped | infra/secrets.py
W15 | Wed 13 Jan | Documents | Statutory documents: death certificates, DHA-1663 notices | app/services/documents/statutory.py
W15 | Thu 14 Jan | Testing | Load test + security regression pass | tests/load/*
W16 | Mon 18 Jan | PHASE 4 GATE | Staging deployed, CI/CD green, offline round-trip demoed, statutory export working — demo-ready for Technical Manager | ALL — gate complete
W16 | Tue 19 Jan | Documents | Lease agreement PDF export | app/services/documents/leases.py
W16 | Wed 20 Jan | Docs | Final documentation pass: API.md, DEPLOYMENT.md, ARCHITECTURE.md, ROADMAP.md | docs/*.md

## Weekly KPIs
Week | Phase | Weekly objective | KPI / acceptance gate | Readiness %
W01 | PHASE 1: FOUNDATION — POLYREPO SPLIT, RBAC & ROUTE INTEGRATION | Create 10 repos under KamiSolutions · unify role model end-to-end · CI template in nexus-infra · pytest scaffold covering verified RBAC/tenant cases | ☑ 10 repos exist under KamiSolutions with nexus-infra's shared CI template wired in ☑ Combined role model importable + tested on both sides ☑ pytest: all 6 verified RBAC/tenant cases automated ☑ CI pipeline passes on push (all repos created so far) | 8%
W02 | PHASE 1: FOUNDATION — POLYREPO SPLIT, RBAC & ROUTE INTEGRATION | Extract nexus-identity-service from the monolith · real login flow · route-level RBAC guard (not nav-hiding) · first legacy routes folded in | ☑ nexus-identity-service deployed independently, gateway routes to it ☑ Login performs a real auth round-trip (no no-op button) ☑ RoleProtected.tsx blocks direct navigation to an unauthorized route ☑ First legacy sub-routes live under (workspace)/* | 14%
W03 | PHASE 1: FOUNDATION — POLYREPO SPLIT, RBAC & ROUTE INTEGRATION | Extract nexus-financials-service · Finance + HR legacy sub-routes integrated · SQLAlchemy models · auth→scope→endpoint integration test across the gateway | ☑ nexus-financials-service deployed independently, gateway routes to it ☑ Finance + HR sub-routes fully folded into (workspace)/* ☑ Auth→scope→endpoint integration test green across the gateway boundary ☑ SQLAlchemy models replace in-memory stand-ins | 20%
W04 | PHASE 1: FOUNDATION — POLYREPO SPLIT, RBAC & ROUTE INTEGRATION | PHASE 1 GATE · nexus-api-gateway live routing to 2 real services · remaining legacy routes integrated · tenant isolation proven · Docker Compose boots all Phase-1 services clean | ☑ PHASE 1 GATE: all acceptance criteria met ☑ nexus-api-gateway proven routing real traffic to 2 independently deployed services ☑ Cross-tenant request proven to 404, never leak data ☑ docker-compose up: zero errors across every Phase-1 repo | 27%
W05 | PHASE 2: COMMAND CENTRE & DOMAIN SERVICES | Command Centre status model designed · legacy routes retired · vehicles router (2nd module) | ☑ Status schema (Operational/Attention Required/Unknown) defined ☑ Legacy flat routes + old Sidebar.tsx removed ☑ Vehicles router live on the financials pattern | 34%
W06 | PHASE 2: COMMAND CENTRE & DOMAIN SERVICES | Command Centre backend live · fake integrations replaced with honest demo-mode states · audit writes transactional | ☑ /api/v1/overview returns real aggregated status ☑ Settings screen shows honest “not connected” for easiPol/EasyPay/Sage ☑ Audit writes confirmed transactional | 41%
W07 | PHASE 2: COMMAND CENTRE & DOMAIN SERVICES | Command Centre frontend replaces fabricated activity feed/AI insight · HR + cases routers | ☑ ExecutiveDashboard shows zero fabricated data ☑ Audit/Activity screen functional (not a decorative chip) ☑ HR + cases routers live | 48%
W08 | PHASE 2: COMMAND CENTRE & DOMAIN SERVICES | PHASE 2 GATE · full schema migrated · no hardcoded demo state left in providers | ☑ PHASE 2 GATE: all acceptance criteria met ☑ Full schema migrated across all modules ☑ Zero hardcoded demo state in any provider | 55%
W09 | PHASE 3: REAL INTEGRATIONS & WRITE WORKFLOWS | First real integration (easiPol sandbox) · write mutators (finance, HR) · attention-required feed live | ☑ easiPol sandbox adapter returns real sandbox data ☑ POST/PUT/DELETE live on finance + HR ☑ Attention-required feed reflects real conditions | 62%
W10 | PHASE 3: REAL INTEGRATIONS & WRITE WORKFLOWS | Webhook processor live · data federation (POPIA) in place · dedicated-tenant provisioning path | ☑ Webhook endpoint verified with signed test payloads ☑ Sensitive policy data never persisted — federation confirmed ☑ Dedicated-tenant provisioning script runs clean | 68%
W11 | PHASE 3: REAL INTEGRATIONS & WRITE WORKFLOWS | EasyPay/Pay@ webhook · BackgroundTasks workflow orchestration · [4-day week: Day of Reconciliation] | ☑ EasyPay/Pay@ webhook receiver tested ☑ BackgroundTasks workflow chain verified ☑ Reduced scope: 4-day week accepted | 74%
W12 | PHASE 3: REAL INTEGRATIONS & WRITE WORKFLOWS | PHASE 3 GATE · [4-day week: Christmas] · documentation sweep | ☑ PHASE 3 GATE: all acceptance criteria met ☑ Reduced scope: 4-day week accepted ☑ API.md + ARCHITECTURE.md drafts exist | 79%
W13 | PHASE 4: PRODUCTION HARDENING & OFFLINE RESILIENCE | [4-day week: New Year] · offline persistence design · staging compose | ☑ Reduced scope: 4-day week + year-end buffer accepted ☑ Offline persistence design reviewed ☑ Staging compose file working | 84%
W14 | PHASE 4: PRODUCTION HARDENING & OFFLINE RESILIENCE | Reconnect queue · deploy pipeline · document generation scaffold | ☑ Offline actions queue and replay correctly ☑ Deploy pipeline runs build→push→deploy ☑ Document generation scaffold renders a test PDF | 89%
W15 | PHASE 4: PRODUCTION HARDENING & OFFLINE RESILIENCE | Batch ingestion endpoint · statutory document generation · load + security test pass | ☑ Batch sync endpoint accepts queued field actions ☑ Statutory documents render correctly ☑ Load test + security regression pass | 94%
W16 | PHASE 4: PRODUCTION HARDENING & OFFLINE RESILIENCE | PHASE 4 GATE · staging demo-ready · lease PDF export · full documentation pass | ☑ PHASE 4 GATE: all acceptance criteria met ☑ Staging demo rehearsed, no P1 bugs ☑ Full documentation set complete | 100%

## Tech Debt & Risks
Risk | Rule | Trigger — when this becomes a problem | Mitigation / status
Three competing role vocabularies [FIXED W01] | There must be exactly one role/permission model. lib/permissions.ts (frontend) and app/core/rbac.py (backend) MUST stay in lockstep — change both in the same commit. | Any week a role or permission module changes and only one side is updated | W01: combined role model shipped, DRIVER + MORTUARY_STAFF added, backend scopes re-keyed to match frontend module:action strings. P1: generate one from the other instead of hand-mirroring.
Route-hiding mistaken for access control [FIXED W02] | Hiding a sidebar item is NOT access control. Every protected route MUST also be guarded server-side by SecurityScopes and client-side by a real RoleProtected wrapper. | First direct-URL navigation to a hidden route, or first pentest | W02: RoleProtected.tsx rebuilt as a real guard (was a 0-byte empty file).
Presenting mock data as a real integration [FIXED W06] | NEVER show a connection status, activity feed, or AI insight that isn't backed by real data. If it's not connected, say “Not connected — demo mode,” never a green checkmark. | Any stakeholder demo where someone asks “wait, is this actually live?” | W06–W07: fake Xero/SharePoint/O365 Settings entries and ExecutiveDashboard's hardcoded activity feed/AI insight replaced with honest state.
Fire-and-forget audit writes | Audit log writes MUST happen inside the same DB transaction as the state change they record, never as a separate HTTP call or best-effort side-write. | Any rejection/failure path — approved state with no audit trail | W06: move audit writes into the same transaction as the workflow state change.
Sensitive third-party data persisted long-term | PII/financial data fetched from easiPol or any third party MUST be data-federated (fetch, mask, short-TTL cache) — never written into Nexus's own long-term tables. POPIA violation otherwise. | First real client onboarding with real policyholder data | W09–W10: Redis short-TTL cache + masked field rendering, cache cleared on session end.
In-memory tenant registry treated as production-ready | The tenant registry (_TENANT_REGISTRY dict) is a placeholder. It MUST be replaced by a real control-plane DB lookup before any real tenant (beyond demo_sandbox) is onboarded. | First real customer signs up | W02: swap in-memory dict for DB-backed lookup — no caller changes required, since routes only depend on the resolved TenantContext.
Hardcoded secrets or demo credentials | NEVER commit API keys, DB passwords, or the demo JWT secret used in local dev. Staging/production MUST use a real secrets manager. | Any week — GitHub secret scanning will flag it | Pre-commit hook: detect-secrets + gitleaks in CI. W15: Secrets management wired for staging.
Legacy and workspace frontend systems left running in parallel | Only one frontend navigation system may exist at a time. Once a legacy screen's content is folded into (workspace)/*, the legacy route MUST be removed in the same change, not left as dead code. | New developer onboarding, confused about which screen is “real” | W01–W05: systematic fold-in of financials/hr/policies/vehicles/leases legacy routes, then removal of the old flat routes + Sidebar.tsx + (tabs) grid.
Polyrepo split adopted before the product proved itself [ACCEPTED DECISION W01] | This roadmap originally planned a modular monolith through Phase 4 and treated microservices as an explicit P2-only decision — the master brief itself warns against splitting “simply because it sounds impressive.” The user overrode that Sept-30 2026, choosing the full GLOW-AI-style polyrepo split from the start. Surfaced as a tradeoff before proceeding (GLOW AI's own split forced a Celery→asyncio rewrite, a PendingTask durability retrofit, and a transactional-audit-write fix — none of which were free) and accepted anyway. | Any week where a service boundary turns out wrong and has to be re-drawn across two live repos instead of two files | W01–W04: identity + financials extracted first (highest-confidence boundaries); remaining services extracted only once each has real code, not speculatively.
Distributed-system complexity: network calls where function calls used to be | Every gateway→service and service→service call MUST handle partial failure (timeout, 5xx, service down) explicitly — a domain service being unreachable must degrade to an honest Unknown status, never a silent 200 with stale/fabricated data (same rule as the mock-integration ban above, now applying to Nexus's own services too). | First time nexus-platform-service's Command Centre aggregates from a service that's mid-deploy or down | W08 (Phase 2 gate): Command Centre's Operational/Attention-Required/Unknown model applies to internal service health, not just third-party integrations. W09: service-to-service auth via gateway-issued short-lived tokens, with explicit timeout/circuit-breaking per outbound call.
Per-repo drift: CI, lint config, or dependency versions diverging across 10 repos | The shared CI workflow template and lint/type-check config in nexus-infra MUST be the single source every service repo references (reusable GitHub Actions workflow), not copy-pasted per repo and left to drift. | Third or fourth service repo created by copy-pasting an earlier repo's CI file | W01: nexus-infra ships the reusable workflow template before the second service repo is created.
Test coverage regression | NEVER merge a PR that drops coverage below the current threshold. Coverage is a one-way ratchet, enforced in CI. | Any merge, especially fast-moving frontend route-integration weeks | CI coverage gate: fail the build if coverage drops below the prior commit's baseline.

## Repo Growth
Figures are AGGREGATED across all ~10 Nexus service repos (gateway, identity, financials, hr, fleet, cases, claims, audit, platform, infra), not one backend repo — reflects the 2026-09-30 polyrepo decision. W00 (single-repo scaffold, pre-split) is actual/verified. All figures from W01 onward are PLANNING TARGETS, not measured actuals — no repos are instrumented for automatic file/LOC/coverage tracking yet, and most of the 10 repos don't exist until the user creates them (see Open Items). Update with real numbers, per repo, as each week completes.
Week | Files (agg.) | Δ Files | Lines of code (agg.) | Test coverage (agg.) | Roadmap readiness
W00 · 30 Sep (today, verified) | ~45 | +45 | ~3,100 | 0% (no tests yet) | 5%
W01 · 09 Oct | ~65 | +20 | ~4,300 | >15% | 8%
W02 · 16 Oct | ~85 | +20 | ~5,600 | >20% | 14%
W03 · 23 Oct | ~105 | +20 | ~7,200 | >25% | 20%
W04 · 30 Oct | ~125 | +20 | ~8,900 | >30% | 27%
W05 · 06 Nov | ~145 | +20 | ~10,600 | >33% | 34%
W06 · 13 Nov | ~165 | +20 | ~12,400 | >36% | 41%
W07 · 20 Nov | ~185 | +20 | ~14,200 | >40% | 48%
W08 · 27 Nov | ~205 | +20 | ~16,000 | >45% | 55%
W09 · 04 Dec | ~228 | +23 | ~18,200 | >48% | 62%
W10 · 11 Dec | ~250 | +22 | ~20,400 | >51% | 68%
W11 · 18 Dec | ~268 | +18 | ~22,000 | >54% | 74%
W12 · 25 Dec | ~280 | +12 | ~23,100 | >56% | 79%
W13 · 01 Jan | ~292 | +12 | ~24,200 | >58% | 84%
W14 · 08 Jan | ~310 | +18 | ~26,000 | >62% | 89%
W15 · 15 Jan | ~328 | +18 | ~27,800 | >66% | 94%
W16 · 22 Jan | ~348 | +20 | ~29,800 | >70% | 100%